## Activités
Model table for import. Remember to select line 3 (the header line) and the lines with your values. The grey values are values for testing
Task |  |  |  |  | Area 1 |  | Area 2 |  | Axis 1 | [8 empty] | Link
ID | Name | Template | Start date | End date | Area 1 | Impact 1 | Area 2 | Impact 2 | Axis | Impact | Execution (O=fixe, 1 = mobile) | Full | Start distance | End distance | ROW | Lenght before | Lenght after | Predecessor ID | Successor ID | Type
A001 | Décapage | Travaux préparatoires | 2020-02-03 | 2020-02-07 | Ilot 01 | 0 | [11 empty] | A004 | A001 | FS
A002 | Terrassement | Terrassement | 2020-02-10 | 2020-02-14 | Ilot 01 | 0 | [11 empty] | A001 | A002 | FS
A003 | Drain | Assainissement | 2020-02-17 | 2020-02-21 | Drains 01 | 0 | Ilot 01 | 1 | [9 empty] | A002 | A003 | FS
A004 | Piste | Terrassement | 2020-01-27 | 2020-01-30 |  |  |  |  | Chaussée 01 | 0 | 0 | 1 |  |  | 0
Note on A3: [Commentaire à thread] Votre version d’Excel vous permet de lire ce commentaire à thread. Toutefois, les modifications qui y sont apportées seront supprimées si le fichier est ouvert dans une version plus récente d’Excel. En savoir plus : https://go.microsoft.com/fwlink/?linkid=870924 Commentaire : Obligatoire

## Param
Booléen | Liens | Unités | Styles
0 | FS | Minutes | Approvisionnement
1 | FF | Heures | Assainissement
| SS | Jour 7h | Caténaire
| SF | Jour 8h | Chaussée
|  | Jour 10h | Equipements
|  | Jour 12h | Essais
|  | Jour 24h | Installation
Ouvrage d'art
Signalisation
Terrassement
Travaux préparatoires
Télécom
Voie Ferrée