## Projet Demo EN Tasks
ID (PM) | Name (PM) | Start (PM) | End (PM) | Calendar (PM) | Area (PM) | Phase (PM) | Start distance (PM) | End distance (PM) | Task Template
2069 | Installation and signaling | 2019-04-17 08:00 | 2019-05-03 12:00 | 5 days 8 hours calendar | Roundabout North | Phase 1 : 1/2 ROUNDABOUT North |  |  | Signalisation
2097 | Sidewalks demolition | 2019-05-22 08:00 | 2019-05-24 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Bordures
2125 | paving milling and asphalt recycling | 2019-05-25 08:00 | 2019-05-29 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Revêtements
2153 | Road widening + drainage | 2019-05-30 08:00 | 2019-06-01 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Chaussée et canalisations
2181 | Coating and backfilling excavations | 2019-06-05 08:00 | 2019-06-07 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Réseaux, remblayages et structure
2209 | Sidewalks and cobblestone installation | 2019-06-08 08:00 | 2019-06-08 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Bordures et pavés
2237 | Topsil levelling | 2019-06-11 16:00 | 2019-06-11 16:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Terre végétale
2265 | Pavement milling | 2019-06-12 08:00 | 2019-06-13 15:00 | 5 days 8 hours calendar | Roundabout North | Phase 1 : 1/2 ROUNDABOUT North |  |  | Fraisage
2293 | Subgrade layer | 2019-06-14 08:00 | 2019-06-15 15:00 | 5 days 8 hours calendar | Roundabout North | Phase 1 : 1/2 ROUNDABOUT North |  |  | Planie
2321 | Base layer | 2019-06-19 08:00 | 2019-06-22 09:55 | 5 days 8 hours calendar | Roundabout North | Phase 1 : 1/2 ROUNDABOUT North |  |  | Couche roulement récap jour
2349 | Sidewalks coating | 2019-06-22 09:55 | 2019-06-22 14:10 | 5 days 8 hours calendar | Roundabout North : Sidewalks 1 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Revêtements
2377 | Signaling | 2019-06-22 14:10 | 2019-06-22 15:00 | 5 days 8 hours calendar | Roundabout North | Phase 1 : 1/2 ROUNDABOUT North |  |  | Signalisation
2405 | Sidewalks demolition | 2019-07-26 08:00 | 2019-07-27 15:00 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Bordures
2433 | Installation and signaling | 2019-07-24 08:00 | 2019-07-25 15:00 | 5 days 8 hours calendar | Roundabout West | Phase 3 : 1/4 ROUNDABOUT West |  |  | Signalisation
2461 | Signaling | 2019-08-22 08:08 | 2019-08-22 12:23 | 5 days 8 hours calendar | Roundabout West | Phase 3 : 1/4 ROUNDABOUT West |  |  | Signalisation
2489 | paving milling and asphalt recycling | 2019-07-31 08:00 | 2019-07-31 15:00 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Revêtements
2517 | Road widening + drainage | 2019-08-01 08:00 | 2019-08-03 14:22 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Chaussée et canalisations
2545 | Coating and backfilling excavations | 2019-08-07 08:00 | 2019-08-08 14:22 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Réseaux, remblayages et structure
2573 | Sidewalks and cobblestone installation | 2019-08-08 14:22 | 2019-08-09 14:22 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Bordures et pavés
2601 | Topsil levelling | 2019-08-09 14:22 | 2019-08-10 14:22 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Terre végétale
2629 | Pavement milling | 2019-08-10 14:22 | 2019-08-14 14:22 | 5 days 8 hours calendar | Roundabout West | Phase 3 : 1/4 ROUNDABOUT West |  |  | Fraisage
2657 | Subgrade layer | 2019-08-14 14:22 | 2019-08-17 14:22 | 5 days 8 hours calendar | Roundabout West | Phase 3 : 1/4 ROUNDABOUT West |  |  | Planie
2685 | Base layer | 2019-08-17 14:22 | 2019-08-21 12:23 | 5 days 8 hours calendar | Roundabout West | Phase 3 : 1/4 ROUNDABOUT West |  |  | Couche roulement récap jour
2713 | Sidewalks coating | 2019-08-21 12:23 | 2019-08-22 08:08 | 5 days 8 hours calendar | Roundabout West : Sidewalks | Phase 3 : 1/4 ROUNDABOUT West |  |  | Revêtements
2741 | Reinforced concrete wall construction | 2019-07-24 08:00 | 2019-09-07 15:00 | 5 days 8 hours calendar | Wall | Phase 3 : 1/4 ROUNDABOUT West |  |  | Mur
2769 | Signaling | 2019-07-23 16:00 | 2019-07-23 16:00 | 5 days 8 hours calendar | Roundabout East | Phase 2 : 1/4 ROUNDABOUT East |  |  | Signalisation
2797 | Installation and signaling | 2019-06-26 08:00 | 2019-06-27 09:55 | 5 days 8 hours calendar | Roundabout East | Phase 2 : 1/4 ROUNDABOUT East |  |  | Signalisation
2825 | Sidewalks demolition | 2019-06-27 09:55 | 2019-06-29 09:55 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Bordures
2853 | paving milling and asphalt recycling | 2019-06-29 09:55 | 2019-07-03 09:55 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Revêtements
2881 | Road widening + drainage | 2019-07-03 09:55 | 2019-07-05 09:10 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Chaussée et canalisations
2909 | Coating and backfilling excavations | 2019-07-06 10:39 | 2019-07-10 09:10 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Réseaux, remblayages et structure
2937 | Sidewalks and cobblestone installation | 2019-07-10 09:10 | 2019-07-11 09:10 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Bordures et pavés
2965 | Topsil levelling | 2019-07-11 09:10 | 2019-07-12 09:10 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Terre végétale
2993 | Pavement milling | 2019-07-12 09:10 | 2019-07-13 15:00 | 5 days 8 hours calendar | Roundabout East | Phase 2 : 1/4 ROUNDABOUT East |  |  | Fraisage
3021 | Subgrade layer | 2019-07-17 08:00 | 2019-07-19 09:10 | 5 days 8 hours calendar | Roundabout East | Phase 2 : 1/4 ROUNDABOUT East |  |  | Planie
3049 | Base layer | 2019-07-19 09:10 | 2019-07-20 15:00 | 5 days 8 hours calendar | Roundabout East | Phase 2 : 1/4 ROUNDABOUT East |  |  | Couche roulement récap jour
3077 | Sidewalks coating | 2019-07-23 16:00 | 2019-07-23 16:00 | 5 days 8 hours calendar | Roundabout East : Sidewalks | Phase 2 : 1/4 ROUNDABOUT East |  |  | Revêtements
3105 | Base layer | 2019-11-15 08:00 | 2019-11-20 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Couche roulement récap jour
3133 | Sidewalks demolition | 2019-09-21 08:00 | 2019-09-25 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Bordures
3161 | Road widening + drainage | 2019-09-25 08:00 | 2019-10-24 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Chaussée et canalisations
3189 | Coating and backfilling excavations | 2019-09-28 08:00 | 2019-10-26 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Réseaux, remblayages et structure
3217 | Sidewalks and cobblestone installation | 2019-10-25 08:00 | 2019-11-06 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Bordures et pavés
3245 | Topsil levelling | 2019-11-08 08:00 | 2019-11-08 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Terre végétale
3273 | Pavement milling | 2019-11-08 08:00 | 2019-11-09 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Fraisage
3301 | Subgrade layer | 2019-11-09 08:00 | 2019-11-14 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Planie
3329 | Sidewalks coating | 2019-11-21 08:00 | 2019-11-21 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Revêtements
3357 | Installation and signaling | 2019-09-20 08:00 | 2019-09-20 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Signalisation
3385 | paving milling and asphalt recycling | 2019-09-21 08:00 | 2019-09-25 15:00 | 5 days 8 hours calendar | Road North Lane | Phase 4 : Road - North Lane |  |  | Revêtements
3413 | Sidewalks coating | 2020-01-25 08:00 | 2020-01-29 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Revêtements
3441 | Signaling | 2019-11-22 08:00 | 2019-11-23 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Signalisation
3469 | paving milling and asphalt recycling | 2019-11-27 08:00 | 2019-11-28 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Revêtements
3497 | Sidewalks demolition | 2019-11-28 08:00 | 2019-11-28 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Bordures
3525 | Road widening + drainage | 2019-11-29 08:00 | 2020-01-02 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Chaussée et canalisations
3553 | Coating and backfilling excavations | 2019-12-04 08:00 | 2020-01-09 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Réseaux, remblayages et structure
3581 | Sidewalks and cobblestone installation | 2020-01-03 08:00 | 2020-01-15 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Bordures et pavés
3609 | Pavement milling | 2020-01-15 08:00 | 2020-01-16 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Fraisage
3637 | Topsil levelling | 2020-01-15 08:00 | 2020-01-16 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Terre végétale
3665 | Subgrade layer | 2020-01-17 08:00 | 2020-01-18 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Planie
3693 | Base layer | 2020-01-22 08:00 | 2020-01-24 15:00 | 5 days 8 hours calendar | Road South Lane | Phase 5 : Road - South Lane |  |  | Couche roulement récap nuit
3721 | Signaling and préliminary works | 2020-02-08 08:00 | 2020-02-12 15:00 | 5 days 8 hours calendar | Road | Phase 6 : Final Paving |  |  | Signalisation
3749 | Wearing course | 2020-02-21 08:00 | 2020-02-21 15:00 | 5 days 8 hours calendar | Road | Phase 6 : Final Paving |  |  | Couche roulement récap nuit
3777 | Wearing course | 2020-02-14 08:00 | 2020-02-15 15:00 | 5 days 8 hours calendar | Road | Phase 6 : Final Paving |  |  | Couche roulement récap nuit
3805 | Wearing course | 2020-02-21 08:00 | 2020-02-21 15:00 | 5 days 8 hours calendar | Roundabout road | Phase 6 : Final Paving |  |  | Couche roulement récap nuit
7798 | Roundabout central plateform installation (earthworks…) | 2019-08-24 08:00 | 2019-08-31 15:00 | 5 days 8 hours calendar | Roundabout central plateform | Phase 3b : ROUNDABOUT Central Platform |  |  | Récapitulative de Zone
10207 | Sidewalks demolition | 2019-05-22 08:00 | 2019-05-24 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Bordures
10235 | paving milling and asphalt recycling | 2019-05-25 08:00 | 2019-05-29 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Revêtements
10263 | Road widening + drainage | 2019-05-30 08:00 | 2019-06-01 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Chaussée et canalisations
10291 | Coating and backfilling excavations | 2019-06-05 08:00 | 2019-06-07 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Réseaux, remblayages et structure
10319 | Sidewalks and cobblestone installation | 2019-06-08 08:00 | 2019-06-08 15:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Bordures et pavés
10347 | Topsil levelling | 2019-06-11 16:00 | 2019-06-11 16:00 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Terre végétale
18859 | Sidewalks coating | 2019-06-22 09:55 | 2019-06-22 14:10 | 5 days 8 hours calendar | Roundabout North : Sidewalks 2 | Phase 1 : 1/2 ROUNDABOUT North |  |  | Revêtements